Elements of the Project Logframe Matrix

|  | Project Intervention Logic | Objectively Verifiable Objectives | Means of Verification | Important Assumptions |
| --- | --- | --- | --- | --- |
| Overall Objective | Goal or higher objective to which the project along with others, will contribute | A set of criteria that will indicate whether the expected results are achieved or not (indicators measure impact at this level) | All source of information necessary to examine indicators (the program evaluation system at this level) | External factors outside the control of the project but crucial for success and which the project should take into account (risks at strategic impact at this level |
| Project Purpose | The expected outcome of the project. The reason why the project designed. Also known as intermediate objective | Measures that describe the accomplishment of the purpose. The return on investment | People events, processes, sources of data for organizing the project evaluation system | Risks regarding program level/outcome/impact |
| Outputs/Results | The outputs of the project. Products and services delivered by the project | Outputs indicators measuring goods and services finally delivered by the project | People, events and processes, sources of data-supervision and monitoring system | Risks regarding project design and effectiveness/result level/ |
| Activities | The actions to be taken by the project in order to transform inputs to outputs | Means: Physical, material, human and soft inputs and resources required to conduct the activities and produce results | Cost Monetary value of the inputs, budget | Risks regarding implementation and efficiency/activity to output) |

Gatira Natural Resource Management Project: Project Logframe Matrix

|  | Project Structure/ Project Intervention Logic | Objectively Verifiable Indicators | Means of Verification | Important Assumptions |
| --- | --- | --- | --- | --- |
| Overall Objective | To promote Sustainable utilization of natural resources | 40% of the NRs in the area sustainably managed and used in 5 years | Impact assessment reports | -Land use policy implemented -Envisaged networking and synergy between the various sectoral agencies practical |
| Project Purpose | Reduced land degradation | 30% of the degraded land in Gatira Kebele protected in 5 years | -Evaluation survey reports -Farmers reports | -Commitment of the regional government continues |
| Outputs: |  |  |  |  |
| Result 1 | Reduced soil erosion | 30% of the degraded land covered by physical conservation methods in 5 years | Field monitoring and evaluation report | -Willingness of the villagers -Availability of materials and professionals |
| Result 2 | Improved cultivation practice | 30% of the degraded land is projected in 5 years | Field monitoring and evaluation report | -Willingness of the villagers -Availability of materials and professionals |
| Result 3 | Improved grazing practice | 30% of the grazing area improved and 30% of the households adopted improved grazing practice in 5 years |  |  |
| Activities: |  | Means | Cost/birr |  |
| Activity 1 |  |  |  |  |
| Activity 1.1 | Check dam construction | Stone, shovel line level, ranging pole string | 17,000 |  |
| Activity 1.2 | Soil bund construction | Hoe shovel, line level, ranging pole, string | 17,000 |  |
| Activity 1.3 | Water-way | Hoe shovel string | 10,000 |  |
| Activity 2 |  |  |  |  |
| Activity 2.1 | Contour farming | Ranging pole, line level, pegs | 10,00 |  |
| Activity 2.2 | Crop rotation | Extension service | 15,000 |  |
| Activity 3 |  |  |  |  |
| Activity 3.1 | Introduction of forage trees | Seeds and Seedlings, Extension services | 15,000 |  |
| Activity 3.2 | Controlled grazing | Extension service | 5,000 |  |