## Slide 1
PART II
Addis Ababa University, School of Social
Work
Project Design and Management (BSSW-
431).
Tenagne Alemu (PhD).
February, 2020.

## Slide 2
Project Proposal Formulation

## Slide 3
Define the distinction between a project and a program:
Program
Project
What is a project formulation?
How can we develop a project?

## Slide 4: Program and project
What is a Project?
A project is a planned undertaking of interrelated and coordinated activities designed to achieve certain specific objectives with in a given budget and period of time.
It should however be , noted that there are different views and definitions of a project. However, the following few characterstics are usually common to all projects:

## Slide 5
1. It operates within a defined objectives, activities, cost, location, target group, and expected outputs
2. It requires the commitment of scarce resources for a specific line of action, such as financial, material and manpower
3. In most cases, it involves special financial arrangements, including loans and grant from different agencies
4. It is designed to improve the socio-economic status of the targeted community

## Slide 6
In view of the above, a project might be defined or explained as a set of organized ACTIVITIES, which yield expected RESULTS that achieve project OBJECTIVES with limited RESOURCES within a limited TIME frame

## Slide 7: Prpgram
What is a development Program/plan?
It is a wider under taking which involves the implementation of several projects to attain sectoral or national objectives.
Effective project preparation and analysis, therefore, must be seen in the framework of broader development plan of a country/sector or Institution.
This implies that projects are part of an overall development strategy/and broader planning process, and there lies the distinction between a project and a programme.

## Slide 8: Origins of projects
Projects could originate from various sources
1. Some may be RESOURCE BASED and stem from the opportunity to make profitable resources
2. Others may be MARKET-BASED arising from identified demand in home or overseas markets
3. Some may be NEED BASED where the purpose is to try to make available to the target community, in a defined area, minimal amount of certain basic material requirements and services.

## Slide 9
What ever is the origin, the governing principles are that a project design must ensure that the proposed intervention will be technically feasible, economically viable and social and culturally acceptable to the intended beneficiaries.

## Slide 10: Introduction to Project formulation
Project formulation is a systematic and logical way of developing cost-effective solutions to development problems
Ex. Think of a problem tree and identified problems, objectives and strategies and stakeholders respectively. This process is to respond to the problems by addressing objectives using possible strategies together with potential stakeholders.
A proposal is a request for financial assistance to implement a project
A proposal must justify each item in the list of things you want, so that a donor agency can decide to provide some or all of the requests
The project proposal must reflect the back ground work you have already done and should be logically set out
Remember that there will be many other organizations and individuals competing for the fund

## Slide 11: …introduction
Before beginning to write a proposal you need to
keep in mind the following points:
Clarify the purpose of the project
Determine the broad project goals, then identify the specific objectives
Identify the requirements of the grant making agency, and be certain that your project fulfils them
Understand what is expected of you from the grant making-agency
Request proposal guidelines, if they have
Note whether there is a funding floor or ceiling

## Slide 12
Make sure that your project plan is based on the communities needs ( baseline data, community based needs assessment results, broad community participation in identification and prioritization of needs, etc have been conducted....)

## Slide 13: The Analysis Phase in relation to Project Formulation
The project formulation begins by analysing the existing situation and developing objectives for addressing real needs of the community.
Remember the problem identification tools in this stage)
The analysis phase is the most critical , yet most difficult phase (MISTAKES AT THIS POINT WILL SPOIL EVERYTHING....) WHY?
Why is mistake in analysis of problems affect the project life at large in the context of a develpoment project planning and implementation?
(group work. It will be presented by group representatives)
The analysis phase consists of four/three stages:
1.Problem/situation Analysis
2. Objectives analysis 3. Stakeholders Analysis and
4. strategy analysis.

## Slide 14: The Analysis Phase Conti
A. Problem/situation Analysis:
Defin: is the process of understanding the status, trends, conditions, and key issues affecting people and people’s livelihoods, ecosystems, or institutions in a given geographic context at any level ( national, regional or local)
Rational for having situation analysis:
1. It helps to clearly identify the needs and concerns of beneficiaries and their livelihoods

## Slide 15
2. It helps to develop goals, objectives, and activities that makes sense for the site’s conditions
3. It helps to assess the likely consequences and implications of a project with in its wider context. (Ex. You cannot implement projects in a given community if your approach is culturally insensitive, etc)
Eg. Condom Promotion in relation to religious beliefs, sexual practices, etc...

## Slide 16: Guiding Principles that should be followed in Analyzing Situations
A good situation Analysis will be:
1. Participatory- shared vision of the problem, shared strategies, etc
2. Outward looking- seeing what others are doing ( explore what is and what is not working and why?)
3. Learning from others:

## Slide 17: Methods and Tools
Some of the methods and tools for situation analysis are:
Review of Back ground documents
Informal meetings ( GATE KEEPERS, ,,,,,,,,)
Stakeholder workshops
FGD
Semi-structured Interviewing
Direct observation
Structured Interviewing
Formulating a problem identification using a problem tree analysis

## Slide 18: Basic Steps
1. Define the boundaries of the area to be included in the analysis ( delineating the area). We cannot conduct analysis in bigger geographic area if we are limited in resources we have at hand.
- should be participatory, using maps, descriptive statistics,
-It will be easier if boundaries are determined as resources available and information is known
2. Prepare for field work- careful planning
- what resources are necessary and /or available
- How much time is required
-Who should take part in the analysis
-What knowledge will the team need

## Slide 19
What site should the assessment team visit? ,etc
3. Select appropriate data collection methods
- What methods will be used to gather relevant information?
- Desk review of published statistics, literature review, etc
- collection of primary data using appropriate tools and approaches

## Slide 20
4. Research and describe the current state and conditions of people and the eco-system
+ Human dimension:
- Health and population (physical and metal health, disease, mortality, fertility, etc)
- Wealth (the economy, material goods, infrastructures, etc)
- Knowledge and Culture (education, state of knowledge about people, systems of belief, etc)

## Slide 21
. Community (rights and freedoms , peace ,crime, social order)
- Equity (distribution of benefits and burdens between males and females, among ethnic) groups, and other socially disadvantaged groups
- Identify and Analyze what problems and issues affect people, the eco-system and institutions in a given geographic context at any level( local, regional, national, and international contexts)

## Slide 22
Issue analysis refers to the external and internal envi’tl factors that are likely to have the greatest impact on the future of the project
Problem Analysis refers to an assessment of the major problems or concerns of the d/t stakeholders of the project
7. Analyze vision and opportunities:
Vision analysis is the process of identifying and analysing what changes the project /program would like to bring about

## Slide 23
8. Assess stakeholders interest, influence and importance
- Stakeholders expectation of the project
- the likely benefit for the different
stakeholders
- What resources stakeholders be able and willing to mobilize to support the project
Which stakeholders interest conflict with other stakeholders and those of the project.

## Slide 24: PROBLEM TREE
Problem tree as mechanism to conduct problem Analysis
What is a problem tree?
Problem tree analysis?
Benefits of using problem tree as a means to a problem analysis
How to form a group for a problem tree analysis
Problem tree as cause-effect relationship in the problem analysis process

## Slide 25: Project identification criteria
Discussion of a project identification criteria
How to see the relationship between a problem identification and project identification

## Slide 26: Components of a project proposal
Project proposal development may not necessarily follow the same outline. WHY? However, for the purpose of this class, the following contents can be used to understand the contents.
Proposal Title
Cover letter
Executive Summary
Introduction
Background/project context
Problem/Need Statement
Project Goals and objectives
Project Outputs
Methods
Inputs
Organization and Administration
Monitoring and Evaluation
Phase out strategy and sustainability
Project Budget

## Slide 27: …components of a Project Proposal
1. Proposal title
  keep interest of your reader in mind
  Make it persuasive, positive and one that will capture attention
2. Cover letter
  Quickly gain the reader attention
  Show why the particular agency should be interested in your proposal
  Convey the importance and urgency of your project
  Keep it short
  Make it look good

## Slide 28: …components of a Project Proposal
3. Executive summary
  It should be clear, concise, and specific
  It should describe who you are, the scope, objective and expected results of your project, and the cost.

## Slide 29: …components of a Project Proposal
Introduction
  In this part of the proposal you introduce your organization
  More often proposals are funded on the reputation of an applicant organization or its key personnel, rather than on the basis of the project’s content alone
  The introduction is the section in which you build your credibility, and make the case that your organization should be supported.
  Establish credibility!!!

## Slide 30: …components of a Project Proposal
Other things to say in the introduction
  How you get started- your purpose and goals
  How long you have been around, how you've grown, and the breadth of your financial support
  Unique aspects of your agency - the fact that you were the first organization of its kind in the nation, etc.
  Some of your most significant accomplishments as an organization or, if you are a new organization, some of the significant accomplishments of your Board or staff in their previous roles
  Your success with related projects
  The support you have received from other organizations and individuals (accompanied by a few letters of endorsement which can be attached in the Appendix).

## Slide 31: …components of a Project Proposal
5. Back ground/Project context
  Background information on the place where the project is going to be located
  It could include the geographic and climatic information, political and administrative scenario and socio-economic status, etc.
  Sometimes, the background information and the introduction can be systematically combined.

## Slide 32: …components of a Project Proposal
6. Problem/Need Statement
The problem /Need statement or situation description is a
key step in grant proposal writing
It is where you convince the donor that the issue you
want to tackle is important and shows that your
organization is an expert on the issue
Use the different needs assessment tools you have learned in the introductory sessions to understand what problem identification and problem means.
In developing Problem/Need Statement, consider the
following points:

## Slide 33: …problem statement
  Make a logical connection between your organization’s background and the problems and the needs which you propose to work
  If the problem is about water, the need should not be about education
  Clearly define the problem(s) with which you intend to work. Make sure that what you want to do is workable-that it can be done with a reasonable time by your agency and with a reasonable amount of money.
  Support the existence of the problem by evidence.
    Statistics,
    statements from groups in your community concerned about the problem,
    from prospective clients,
    from other organizations working in your community and from professionals in the field.

## Slide 34: …problem /need statement
  Be realistic-don’t try and solve all the problems in the world in the next six months
  Don't assume the donor knows much about your subject area
  Describe why this need/situation is important
  Describe your issue in as local context as possible or organization focus

## Slide 35: Problem Analysis
Problem analysis identifies the negative aspects of an existing situation and establishes the ‘cause and effect’ relationships between the problems that exist. It involves three steps:
1. Precise definition of the framework and subject of analysis;
2. Identification of the major problems faced by target
Identifying the real problems of beneficiaries
groups and beneficiaries (What is / are the problem/s? Whose problems?);

## Slide 36: Project Proposal conti……..
7. Project Goals and Objectives
Rules for Setting a Project Goal
. There should be only one goal per project.
2. The goal should be connected to the vision for development.
3. It is difficult or impossible to measure the accomplishment of the goal using measurable indicators, but it should be possible to prove its merit and contribution to the vision.
A well prepared proposal has the continuity-a logical flow from one section to another
Your introduction can establish the context of your problem statement
Similarly, the problem statement will prepare the funding source for your logical goals and objectives
The goal and objectives are the outcomes of the planned project, and they answer the question, how would the situation look if were changed

## Slide 37: …goal
A goal is a broad statement of the ultimate result of the change being undertaken
e.g.
    Decrease prevalence of STIs among out of school youth
    Increase availability of resources to address the problem of adolescent pregnancies
  These are not measured
Goal is a result that is some times unreachable in the short term
Goal is often written for the organization as part of a long range planning process

## Slide 38: …objectives
An objective is a measurable, time specific result that the organization expects to accomplish as part of the grant
It is much more narrowly defined than a goal
Like a goal the objective is tied to the need statement
Good objectives also answer the following five simple questions:
When: Time
Where: Plan of action
Who: Client
What: Expected Outcome
How much: Percentage problem is reduced

## Slide 39: …objectives
Objective should be SMART
  Simple/Specific-they measure only one thing, not many different aspects of an objective. To keep them simple, break down complex objectives into several sub-objectives.
  Measurable- objectives need to be accurately measured to be useful, but they should be aimed at program usefulness, not "developing new knowledge" for the sake of the knowledge itself.
  Appropriate- "technically adequate" (according to current understanding and practices) and "important" (it measures something that will actually reflect the success of some aspect of the program or project).
  Realistic - the objectives should be set at levels that can reasonably be attained during the specified time period.
  Time-bound - the time frame within which the objective will be accomplished must be clearly specified.

## Slide 40: …objectives
Examples of SMART Objectives
  By the end of the project, at least 35% of the regular participants in the anti- AIDS clubs will report that they have changed some risky behavior after learning about the risk of AIDS“
  Increase condom use among urban youth, ages 18 to 25, (by 20% in the next year.
  Increase reduction of sexual partners among in school youth from the current three to one by end of the project.

## Slide 41: Components of a Project Proposal
9. Methods
  It is the part of the proposal where the reader should be able to gain a picture in his/her mind of exactly how things work to achieve the stated objectives
  For example one of the strategy used to achieve the objective given above is through establishing anti AIDS clubs
  Relevant activities might be:

## Slide 42: Components of a Project Proposal
10. Project Inputs
  Inputs are the financial (budgets), material (equipment, logistics) and human resources (project team, partner organizations) necessary for carrying out the activities.
  If the project is to be "sustainable", then the identification of key local resources is likely to be crucial to the achievement of sustainability.
  Human, material, financial, ( how? Remember all the participatory discussions since the situation analysis phase…….)
  Local Resource Identification= Ownership=
  sustainability=riplicability
  Make input requirements as detailed as possible and justify any specific requirements to avoid, for example, unsatisfactory substitutions of equipment at a later stage. ( replacing what was originally in the input plan by something else i.e promising some material inputs or some professional inputs by others which might not be comparable .).

## Slide 43: Components of a Project Proposal
Project Organization and Administration
  The project's internal organization as well as its relations to partner organizations have to be expressed in hierarchical and operational terms.
  Are the collaborations with institutions or individuals, permanent or occasional, contractual or informal.
  Identify type of relationships..( permanent, and temporary r/sps)
  Indicate where the project is located; headquarters and/or decentralized units.
  Working relationship between staff members within organizations.
  Show working r/s

## Slide 44: 12. Monitoring and Evaluation
What information are needed for monitoring?
Who is responsible to conduct M&E, tools to conduct M&E, purposes of M&E, etc
Depending on the size of the project, monitoring and evaluation could include the following information: -
  Who should monitor and evaluate?
  What to monitor and evaluate?
  How to monitor and evaluate?
    Monitoring and evaluation indicators
  Resource requirements,

## Slide 45: Evaluation
Evaluation is an “assessment, as systematic and objective as possible, of an ongo-ing or completed project, programme or policy, its design, implementation and results. The aim is to determine the relevance and fulfilment of objectives, develop-mental efficiency, effectiveness, impact and sustainability. An evaluation should pro-vide information that is credible and useful, enabling the incorporation of lessons learned into the decision-making process of both recipients and donors

## Slide 46
An evaluation can be done during implementation (mid-term), at its end (final evaluation) or afterwards (ex post evaluation), either to help steer the project or to draw lessons for future projects and programming. Ex ante evaluation refers to studies during the preparatory phases of the project cycle (pre-feasibility or feasibility studies).

## Slide 47: Major Principles of Evaluation
Impartiality & independence of the evaluation process in its function from the process concerned with policy making, the delivery and management of assistance ( separation of evaluation and responsibility for the project/ programme/policy)
Credibility depending on expertise and independence of the evaluators & transparency to be sought through an open process, wide availability of results, distinction between findings and recommendations
Usefulness: relevant, presented in a clear and concise way, reflecting the interests and needs of the parties involved, easily accessible, timely and at the right moment
improved decision-making
Participation of stakeholders (donor, recipient...); if possible: views and expertise of groups affected should form integral part of the evaluation;
Involving all parties

## Slide 48: Types of Evaluations
Evaluations can take place:
when the project is still under way: such interim evaluation are usually under-taken at mid-term (mid-term evaluation), to review progress and propose alterations to project design during the remaining period of implementation;
2. at the end of a project (final or end of project evaluation), to document the resources used, results and progress towards objectives. The objective is to generate lessons about the project which can be used to improve future de-signs;
3. a number of years after completion (ex post evaluation), often focusing on impact.

## Slide 49: Evaluation Criteria
Relevance : The appropriateness of project objectives to the problems that it was supposed to address, and to the physical and policy environment within which it operated, and including an assessment of the quality of project preparation and design.
The logic and completeness of the project planning process, and the internal logic and coherence of the project design can be seen through evaluation.

## Slide 50
Efficiency : The fact that the results have been achieved at reasonable cost, i.e. how well inputs/means have been converted into results, in terms of quality, quantity and time, and the quality of the results achieved. This generally requires comparing alternative approaches to achieving the same outputs, to see whether the most efficient process has been adopted.

## Slide 51
Effectiveness: An assessment of the contribution made by results to achievement of the project purpose, and how assumptions have affected project achievements.
Impact: The effect of the project on its wider environment, and its contribution to the wider sectoral objectives summarised in the project’s overall objectives, and on the achievement of the overarching policy objectives.

## Slide 52
Sustainability : An assessment of the likelihood of benefits produced by the project to continue to flow after external funding has ended, and with particular reference to factors of ownership by beneficiaries, policy support, economic and financial factors, socio-cultural aspects, gender equality, appropriate technology, environmental aspects, and institutional and management capacity.

## Slide 53: Benefits of M&E
Organizational learning
Accountability
Opportunities for feedback
Celebrate success
Informs decision-making to improve performance

## Slide 54: The Power of Measuring Results
“If you do not measure results you cannot tell success or failure.
If you cannot see success, you cannot reward it.
If you cannot reward success, you are probably rewarding failure.
If you cannot see success, you cannot learn from it.
If you cannot recognize failure, you cannot correct it.
If you can demonstrate results, you can win public support.”

## Slide 55: Complementary Roles of Monitoring and Evaluation
Monitoring
Reminds us of project or programme objectives
Links activities and their resources to objectives
Routinely collects data on performance indicators
Compares actual results with targets
Reports progress to managers and alerts them to problems

## Slide 56
Evaluation
Analyzes why intended results were or were not achieved
Assesses specific causal contributions of activities to results
Examines implementation process
Assesses the overall reason for and relevance of project
Provides lessons, highlights significant accomplishments, and offers recommendations for improvement

## Slide 57: In a nutshell…
MONITORING = ONGOING
  Tracking changes in program performance over time
EVALUATION = ONE POINT IN TIME
  Assessing whether objectives have been met
  Assessing extent to which program is responsible for observed changes

## Slide 58: Components of a Project Proposal
Phase Out Strategy and Sustainability
  Local institutions or communities who will takeover the project have to be identified and indicated
  if you continue this project in the future, how will it be supported?

## Slide 59: Assessing the Assumptions
Assess the importance of the external factors based on conclusions arrived at after analyzing the following;
The external factor that answers almost uncertainly to the question if it will be realized, must be left out.
The external factor that answers likely should be included as an assumption.
The one that seem unlikely must be redesigned

## Slide 60: Ensuring Programme/Project Sustainability
Once the intervention logic has been established, it is important to ascertain that the sustainability of the intended programme/project benefits are analyzed.
Sustainability means the degree to which the benefits or long term impact of a programme or project are carried beyond the lifecycle and after all the input processes or the major part of donor assistance have been completed.
The PM approach ensures that the sustainability factor is in-built in the design process rather than being hastily considered as an add-on concern at programme or project completion
A timely sustainability analysis will allow for additional outputs or activities to be included in the programme or project during the planning phase in order to increase the chances of sustaining the benefits

## Slide 61: Assess programme or project sustainability
The following factors need to be considered;
Ownership by beneficiaries:
Policy framework
Appropriate technology
Socio-cultural issues
Gender balance
Institutional and management capacity

## Slide 62: Means of Verification
There must be a means by which to show evidence that your work has been done
The means of verification define the sources of information for verifying progress in achieving set targets.
This entails defining the process of data collection throughout the programme/project cycle.
Means of verification are the instruments providing information that makes it possible for indicators to be monitored and verified
When indicators are formulated, the source of information and means of collection should be specified

## Slide 63: Reporting
Programme and Project Managers will want to review progress very frequently, say monthly against contracted budgets and planned activities
A few selected items plus aggregated data on equipment and materials are considered key indicators for reporting on progress recorded
For monitoring to be described as complete and successful, information collected must be communicated – in the right form, to the right person and at the right time
This enables timely and appropriate management decision making

## Slide 64: Progress Reports
Progress reports are periodic summaries of progress made in the implementation of programme or project activities, incorporating key information from the physical and financial indicators
The report should cover the following areas;

## Slide 65: Progress Reports
Summary of the current status of the programme or project against indicators for programme or project purpose and outputs
Major activities undertaken during the reporting period as compared to the activity schedule
Programme or project expenditure for the reporting period as compared to the budget and cost schedule
Estimates of the number of clients and beneficiaries reached out to during the period
Current and anticipated problems and constraints encountered during the period and how they have been handled or planned to be handled
Planned major activities and schedules for the next period

## Slide 66: Components of a Project Proposal
14. Project Budget
  Clearly depict how much money is needed and how it will be used
  The budget should include sources and uses of funds
  Sources of funds should include names of other funding organizations and amounts pledged or received as well as amounts still needed to be raised and possible sources of funds.
  Indicate the time period covered by the budget
  Indicate if requested expenses are one time or ongoing
  Make sure that you have accounted for all costs
  Finally, make sure all the numbers add up.

## Slide 67: Components of a Project Proposal
Appendix
  Audited financial statement
  Indication of legal registration status
  Roaster of board of directors
  Organizational structure
  Organization budget
  Summary chart of key activities/action plan
  Letter of support or endorsement
  Resumes
  Job descriptions
  Last annual report, if any
  Memorandum of association
  Relevant project agreement with concerned government bodies

## Slide 68
Determine which project ideas have the best chance of being funded.
Form a planning team that includes those affected by the project, community leaders, key staff and volunteers, and other organizations with similar or complementary projects
Conduct through research to determine funding sources interested in the project.
Read all funding source materials to ensure their directions are followed while writing the proposal.
Prepare the proposal components by stating the need or problem being addressed, the objectives and methods to meet the need, how the project will be evaluated and funded in the future, and the budget.

## Slide 69: Proposal Checklist
Prepare the final proposal components, including the introduction, summary, cover letter
Determine those features in the project that may set it apart from others and will appeal to the donor. Make sure those features are highlighted for the funding agency.
Ensure the proposal is clear and well written by having at least one person review it and give you feedback
Include the appendices requested by the donor
Check donor deadlines and the number for proposal copies to be submitted in order to meet their requirements
Give copies of the proposal to the planning team and other individuals or groups who should be aware of the project