## Slide 1: PART I Addis Ababa University Project DESIGN AND Management ((BSSW-43). Instractor: Tenagne alemu (PhD) February, 2020

## Slide 2: The concept of Project/Program Management
A project is defined as an undertaking for the purpose of achieving established objectives within the constraints of time and budget.
In other words, a project can be described as a process of providing inputs over a period of time using resources provided to carry out activities and produce outputs (results) in order to achieve defined objectives (project purpose) or as a set of related activities planned to take place during a defined time frame and budget to improve the situation of a specific group of people.
A programme is a much broader concept involving a collection of interrelated projects and activities, with a variety of methods of intervention contributing to an overall goal. A programme will thus have a range of strategies working towards defined outcomes.

## Slide 3: Project defi
A project is a unique endeavour designed to produce a set of achievable
it is a one time effort limited by time and budget or resources and performances.
THE NATURE OF PROJECTS:
Project involves the investment of scarce resources in expectation of future benefits.
It involves a single desirable purpose or end item or result.
Every project is unique– i.e, projects cannot be repeated in the same manner.
Has a defined life span with a beginning and an end.

## Slide 4: The nature conti…
Involves doing something never been done before.
It utilizes skills and talents from multidisciplinary teams.
A project has risks.
Have time and cost constraints
It is dynamic in nature and the team interaction and experiences are part of learning.

## Slide 5: Distinctions between program and projects
Program projects
= Scope –wide, diverse = Narrower or limited
Location- diffused, wide = Specific
Life time- Non-time bound = Time bounded
Beneficiaries-Not specific = Specific
Resources- Larger budget = limited budget

## Slide 6: Management
Management refers to the act of structuring social processes in order to achieve predetermined objectives.
It is broken down into key functions such as agreeing on objectives, planning, decision making, motivating, organizing, steering, monitoring and informing.
The performing of these functions and the resultant task throughout the programme or project cycle constitutes what is known as management.

## Slide 7: Programme/Project Management
Programme or project management describes management of activities and decision making processes used during the life of a programme or project.
In essence, PM is a way of thinking through the life cycle of a programme or project and consists of a set of design and management concepts, techniques and tasks that is used to support informed decision making and to strengthen the management of programmes and projects.

## Slide 8: The Programme/Project Manager
Programme and Project Managers play a central and catalytic role in ensuring that interventions go through their life cycle and produce the desired outcomes.
Seeing that the methodology of managing programmes and projects is gradually shifting from traditional programme or project management to a more complete and complex cycle management. Managers as well need to make a shift towards becoming programme or project cycle managers in order to be able to better articulate the concept.
Managing programmes and projects is a complex methodology and therefore requires mastery of the skills and techniques involved, especially with regards to the understanding of the logic of intervention and use of the Logical Framework Analysis.

## Slide 9: Changing roles of project managers
Controlling and directing
Imposing norms
Creating certainty/FIRMNESS
Telling
Vertical/line authority
Solving problems
Area and scope management
Empowering and releasing potential
Releasing creativity
Managing uncertainty
Listening
Matrix programme or project management
Creating opportunities
Collaboration and partnerships
Then
Now

## Slide 16: Stakeholder Analysis( SHOULD BE SEEN LATER)
Stakeholders refer to individuals, groups of persons or entities that have interest or a relationship with your development partnership
Primary stakeholders: This category includes those whose interest lies at the heart of the programme or project. Their involvement is indispensable. (ex. Beneficiaries).
Secondary stakeholders: This category normally provides the primary support for the programme or project and from it you are likely to identify partners for the development partnership. (donors).
Tertiary stakeholders: This category might not necessarily be directly involved but their involvement might become necessary at a later stage. (indirect beneficiaries).

## Slide 17: Roles and Responsibilities
Defining specific roles and responsibilities for each of the development partners will enable you identify how and when each of them would be involved at the different phases of the programme or project cycle.
Some of the partners may have to play keys roles while others may have to play a supporting role.
Once the roles and responsibilities for each partner have been established the information can be used to draw up terms of reference for the development partnership.

## Slide 18: Structure of Programme/Project Life Cycle
What is a project life cycle?
The life cycle of a programme or project describes the process that starts from the conception of an idea through planning to completion of the programme or project activities.
According to this concept a programme or project goes through different phases. The number and duration of each phase vary according to the nature of the programme or project.
The structure of the cycle does not follow any unique pattern. However, the generic structure usually consists of six phases

## Slide 19: Program/Project Cycle
The cycle starts with an idea which is a sequence or pattern through which projects are developed into a working plan that can be implemented, monitored and evaluated.
The basic components of a programme or project cycle are generally identical but how their formulation varies.
The breakdown of the programme or project cycle into phases helps to orientate managerial action.
The PM method was introduced to improve quality of programme or project design and management and consequently the quality of development aid.

## Slide 21: Main Phases
The programme or project cycle is a diagrammatic description of the sequence of how interventions are planned and carried out, beginning with an idea, which leads to a strategy for a specific action, which then is formulated, financed, implemented and evaluated with a view to improving the situation and taking further action.
The cycle defines the various phases in the life of the programme or project, with a well defined process of involvement of different stakeholders, management activities and decision making processes that need to happen before, during and after implementation.

## Slide 22: The Project/Program Cycle
Programming
Identification
Formulation
Financing
Implementation
Evaluation

## Slide 23: Importance of knowledge of different phases
Help you think through the key steps of setting up and running a programme or project (helps to avoid confusion and later failure).
Help you to formulate problems and ideas into programmes or projects ( transtitioning problems in to projects/programs).
Ensure that programmes and projects are documented and prepared so that they are technically and institutionally feasible
Ensure that programmes and projects are sustainable
Help to improve monitoring and evaluation
Encourage and improve the process of learning by experience

## Slide 24: Before starting Implementation
Programming
Identification
Formulation
Financing

## Slide 25: Programming
Programming is concerned with
  analyzing problems, constraints and opportunities, establishing general principles and guidelines,
  agreeing on sectoral and thematic focus and outlining of programme or project ideas.
The main actors involved at this stage are the implementing organization and the affected group

## Slide 26: Identification
This phase consists of the framework
  for analysis of problems, needs and interest of potential stakeholders and the identification of options to address the problem.
  The analysis will also help in understanding the programme or project context with regards to its relevance, feasibility and sustainability and the chances of funding based on comparison of the programme/project objectives with the funding criteria of potential partners.
The implementing organization plays a leading role during this phase

## Slide 27: Formulation
Also known as the design phase, involves
  an intensive participatory process that brings together the principal actors into a planning process
  allow for relevant programme or project ideas to be developed into operational issues such as activity and resource scheduling.
  All significant aspects of the idea are studied, taking into account stakeholders’ views, relevance to the problem, feasibility and other issues.

## Slide 28: …

## Slide 29: Financing
Once decision is made to carry out the project proposal is put up, aimed at securing funding for the proposed programme or project.
The submitted proposal is subject to a final appraisal and review by the potential donor, leading to a decision on whether to approve the programme or project for funding or not.
If it is approved, then the phase concludes with the signing of a formal agreement between the implementing organization and the donor partner

## Slide 30: Implementation
Implementation involves carrying out programme or project activities as planned.
  ensure that the programme or project stays on course, constant and proper monitoring and mid-term evaluations are necessary to measure the extent to which results and objectives are being achieved,
  identify any shortfalls and to enable adjustments to the changing circumstances.
  During this phase, all the actors get involved directly or indirectly

## Slide 31: After Implementation
Evaluation
  Evaluation is carried out to measure the results of the intervention in relation to the objectives
    whether they were achieved or not and helps to determine the relevance, effectiveness, efficiency and impact.
    Evaluation should provide information that is credible and useful, allowing for valuable lessons learned during the course of the programme or project to be incorporated into decision making and to influence further action.
    The results of evaluation would determine if the intervention should be carried on, terminated or if the strategy should be changed.

## Slide 32: Programme/Project Spiral
Effective and efficient programme or project cycle management provides a framework for on-going learning from the process and consequently improvement of interventions
This explains the fact that development work is never a straightforward process and in reality does not follow the ideal “programme or project cycle.” Since all development work involves continuous learning and change at every stage in the process it is reasonable to think in terms of a programme or project spiral rather than a cycle
The spiral is presented as a changing process whereby experience gained through different activities is systematically incorporated into future ones.

## Slide 33: LOGICAL FRAMEWORK APPROACH TO PCM
PCM and the Logical Framework Approach

## Slide 34: What is Logical Framework Approach
The LFA is a way of thinking and an effective technique for enabling stakeholders to identify and analyze problems and to define objectives and activities that need to be undertaken to address problems identified
Programme and project planners use the logframe structure to test the design of a proposed intervention to ensure its relevance, feasibility and sustainability.
The logframe as a key management tool provides the basis for the preparation of activity or implementation plans and for the development of a monitoring system and a framework for evaluation

## Slide 35: LFA as a Dynamic Management Tool
The LFA is an essential tool used by those who prepare and implement projects to structure and formulate their ideas and to present them in a clear and standardized format.
Quality of Joint planning depends on the:
  Information available
  The skills of the planning team
  Consultation of a balanced representation of stakeholders
  In depth consideration for lessons learnt
The log frame as such is not a rigid instrument but a dynamic tool that needs to be re-assessed and revised

## Slide 36: LFA as an Embedded Structure of the PCM
logframe can only serve as a useful and dynamic management instrument with limited shortcomings when it is embedded within the broader context of the PCM approach
by itself alone, the logframe is characterized by potential flaws and limitations
The PCM approach should indeed allow for constant integration of changes and new insight that are the result of analyses and experiences gained during the programme or project cycle
Within PCM such integration and adaptation will be undertaken in a flexible but organized, transparent and negotiated manner. Only in this context, PCM guided learning can outweigh the risks of rigidity

## Slide 37: The Interlinked Phases of the LFA
The logframe comprises of two phases which are carried out progressively during the identification and formulation phases of the programme or project cycle
Using the LFA during identification (analysis) phase helps to ensure that programme/project ideas are relevant, while during the formulation (planning) phase it helps to ensure feasibility and sustainability
Basically the approach can be ear-marked by the following
  Stakeholder participation
  Logicality in the design process
  Reaching consensus based on mutual understanding
  Consistency in implementation and decision making
The approach consists of a combination and interlink between the Analysis phase and the Planning phase

## Slide 38: Two different phases of ANALYSIS IN PROJECT MANAGEMENT
Analysis phase
  Stakeholders Analysis
  Problem analysis
  Objective analysis
  Strategy analysis
  SWOT Analysis

## Slide 39: Analysis Phase
It deals with the assessment of existing situation:
provides the basis upon which the existing situation is assessed to develop a vision of the future desired situation and to select the strategies that will be applied to achieve them
Assessment is best done in a group/workshop environment where all key stakeholders are represented and problems and issues are discussed openly (Discuss why grouping is relevant).
The four stages of analysis include stakeholder analysis, problem analysis, analysis of objectives and strategy analysis

## Slide 40: Stakeholder Analysis
Define what stakeholders means: (individuals, groups, organizations, community groups, gov’t institutions, religious institutions, associations, clubs, local organizations,) etc
a systematic way of assessing the role that different stakeholders have to play in your programme or project (discuss how the above bodies will impact your project or being impacted negatively or positively by the project)
Stakeholders may be affected positively or negatively by programme or project activities and this is based on how each of the stakeholders perceives the existing situation
They may either be individuals, groups, communities or institutions
Understanding all those who would be affected and how they will be affected sets a good base for analyzing the problem that your programme or project seeks to address
This information is important in every aspect of programme or project management.
Important to do a stakeholder analysis in terms of particular projects/ programs rather than implementing organization
(example, assess potential stakeholders for the care and support project to OVCs) than assessing the organization implementing the OVC project).

## Slide 41: Gender and Rights Based Considerations
Programme or project relevance, feasibility and sustainability are likely to be much greater when major stakeholders are consulted during the analysis phase and are actively involved in the planning process.
Right holders deserve to be consulted and involved in any intervention that affects them, either positively or negatively
certain programme or project activities may be impossible to realize if both women and men have not been consulted
It is essential therefore to analyze the potential impact of an intervention on men, women, children, ethnic minorities, the disabled and other social groups and their rights given due consideration before important decisions are taken

## Slide 42: Problem Analysis
Assessment of the negative aspects of an existing situation and representing the relationship that exists between causes and effects. It can be done in several ways like: through community group discussions, interviewing of people, participant observation, using semi structured interview guides/data collection instruments and using a problem tree analysis. For our purpose we will see the problem tree approach in problem analysis.
Best done in a group/participatory workshop involving representatives of all the stakeholder groups
The actual needs of the affected group should first be established, the major or central problem faced by the affected group is identified and then the process follows by identifying the causes to the problem and the effects they produce
Problems do not exist all by themselves; they are always part of a cause-and-effect relationship
If you identify a problem wrongly the solution is most certainly going to be wrong, reason why problems must be expressed in concrete and factual terms and not wrapped up in general and vague language

## Slide 43: STEPS IN UNDERTAKING A PROBLEM ANALYSIS
The following simple procedures can be follow to work on the problem analysis:
1. Formulate problems
A. Stakeholders brainstorm suggestions to identify a focal problem, that is, to describe what they consider to be the central point of the overall problem.
B. Each identified problem on written down on a separate card.
Display them where all participants can see them.
Try only to identify existing problems, not possible, imagined or future ones.
What is a problem? A problem is not the absence of a solution but an existing negative state. Crops are infested with pests is a problem. No pesticides are available is not.

## Slide 44
2. Select one focal problem
A. The participants should discuss each proposal and try and agree on one focal problem
What is focal problem? One that involves the interests and problems of the stakeholders present.
If agreement can not be reached, then:
- arrange the proposed problems in a problem tree according to the casual relationships between them;
- try again to agree on the focal problem on the basis of the overview achieved in this way;

## Slide 45: 3: Develop the problem tree
A. Identify immediate and direct causes of the focal problem.
B. Identify immediate and direct effects of the focal problem.
C. Construct a problem tree showing the cause and effect relationship between the problems.
D. Review the problem tree, verify its validity and completeness and make any necessary adjustments.
In developing problem tree, the cards can be moved so that:

## Slide 46: How to do a problem analysis
Core problem
Cause
Effect
Effect
Effect
Effect
Cause
Effect
Cause
Cause
Cause
Root cause
Root cause
The Problem Tree

## Slide 47: Problem Tree
When the process is completed, the diagram will take the structure of a tree
Problem Tree represents a comprehensive picture of the existing negative situation, with the causes representing the roots, the core problem representing the trunk and the effects representing the branches of the tree

## Slide 48: Importance of Problem Analysis
Problem analysis is particularly important:
  In helping to analyze a given situation
  In identifying key issues to focus on
  In clarifying the causes and effects of a problem
  In setting programme/project objectives through participation of all stakeholders
Discussing the problem itself is important and can lead to greater understanding of the issue surrounding it

## Slide 49: Assignments
try to consider any social or development problem that needs social work intervention.
1. Analyze the problem using a problem tree approach.
Please present a problem tree which may require addressing the effects of the problem than the causes.
Please present a problem tree which may require to better address the causes than the effects.
Identify a situation where it might be better to address the cause and effects of the problem.

## Slide 50: Analysis of Objectives
An assessment and projection of the positive aspects of a desired future situation
It looks at the possible options to solve the identified problem.
The assessment involves converting the problems (causes and effects) into objectives that the intervention will seek to achieve and establishing the relationship that exists between the means (methods) and the ends (results)
Objectives clearly express what the programme or project is trying to achieve so that activities can be designed to meet them

## Slide 51: Analysis of Objectives…
If objectives are clear, everyone has the same idea why they are engaged in specific activities and progress related to achieving the objectives can be measured.
As things change and develop, it may become necessary to alter the objectives on the basis of lessons learnt or changes that occur during implementation

## Slide 52: How to do Objectives Analysis
The procedure for doing objectives analysis is much simpler once the problem analysis has been done and the problem tree formulated
Objectives tree looks a direct positive reflection of the problem tree
The analysis of objectives should be carried out in the same workshop and with the same participants that did the problem tree

## Slide 53: Objective Tree
Changed Situation
Skills
Positive Effect
Positive Effect
Positive Effect
Positive Effect
System
Positive effect
Best Practices
Lessons
Manuals
Major Action
Major Action
The Objective Tree
Means
End

## Slide 54: Strategies Analysis
Strategy analysis involves deciding on appropriate strategies for achieving objectives
  which of the objectives need to be tackled and which ones need to be left out.
It involves deciding on the programme/project purpose, the goal and feasibility of each intervention.

## Slide 55: How to Choose the Strategy Options
From the objectives tree identify those objectives that are not desirable or feasible.
Objectives of the same kind should be clustered into possible strategies. Agreements should be obtained that the selected strategies are all relevant to solving the core problem.
Arrange strategies as to produce a hierarchy of outputs, purpose and outcomes

## Slide 56: Considerations when doing strategy analysis
What combination of activities or interventions is likely to improve or change the existing situation and ensure sustainability?
Which options best encourage and promote local ownership?
Which are the most cost effective options?
What are the resources or funding potentials available
What other interventions are being carried out
Once identified, the selected strategies can then be transferred into the first column of the logframe to make up the beginning of the construction of the logframe matrix

## Slide 57: The Logframe Approach
Stakeholder Analysis: Identify stakeholders, their interest & priorities, how they are consulted & their participation in the programme or project
Problem Analysis: Identify key problems, constraints and opportunities & determine the relationship between causes & effects
Objectives Analysis: Transforming problems identified into objectives to be achieved and determining the relationship between the means (methods) & the ends (results
Strategies Analysis: Map out different strategies to achieve objectives and determine overall goals and programme/project purpose
Intervention Logic: Identify & define programme or project elements, test the internal logic & formulate objectives in measurable terms
Activity Planning: Decide on what activities need to be done & their sequence & dependency of one to the other, set time frames & milestones & assign responsibilities
Resource Allocation: Matching activity plans with input schedules & developing a budget.
Monitoring & Evaluation: Define indicators for measuring progress, means of verification & decide on frequency of M&E,
Analysis Framework
Planning Framework

## Slide 58: Preparing the Logical Framework – Programme/project Design Matrix (PDM)
The PDM is a format that sets out the basic structure of a programme or project in table format with a four by four matrix and defines the logical interrelationship between the different elements
The PDM also known within other development circles as the logical framework matrix (LFM) is an analytical tool that helps to present the relationships between activities, outputs, programme/project purpose and overall goal in a logical and summarized format
It is an important tool, especially for understanding programmes and projects supported by different donors

## Slide 59: Presentation of the PDM or LFM
Programme/Project Description | Objectively Verifiable Indicators | Means of Verification | Important Assumptions
Overall Goal Contribution to a broader impact, programming framework or policy | How will the overall goal be measured in quantity, quality and time? | Data collection - how when & by whom? | 
Programme/project Purpose Direct benefits to the target groups | How will the specific objectives be measured in quantity, quality & time? | Data collection - how when & by whom? | If purpose is achieved, what assumptions must hold true to achieved overall goal
Outputs Tangible products or services delivered by the programme or project | How will the outputs be measured in quantity, quality & time? | Data collection - how when & by whom? | If outputs are achieved, what assumptions must hold true to achieved the purpose
Activities Tasks that have to be undertaken to deliver the desired results | Means | Costs | If activities are completed, what assumptions must hold true to achieved outputs

## Slide 60: Interpretation of the logic of PDM
The matrix in its basic form is a table consisting of four columns and four rows.
For better understanding, the logic must be read vertically and horizontally.
The vertical logic identifies what the programme or project intends to do and clarifies the causal relationships, important assumptions and uncertainties that are beyond the control of the programme or project.
The horizontal logic has to do with measuring the effects and the input through the specification of key indicators and means of verification
Notes: Overall Goal: The overall goal defines a broad development objective to which the programme or project contributes in terms of its impact or broader benefits to society .
Programme/project Purpose: The programme or project purpose, which is also known as the specific objectives should address the core problem and be defined in terms of the intended direct benefits to the beneficiaries or target group .
Outputs: Also referred to as results, the outputs describe the product of the intervention which accords benefits to the target group. It describes the added value generated by the programme or project as a result of the activities carried out.
The outputs should address the main causes of the problem that the target group is confronted with.
Activities: Activities describe how the programme or project is implemented, what it will do to produce the expected or desired output.

## Slide 61: Project Structure - Levels of Objectives
Overall Goal: defines a broad development objective to which the programme or project contributes in terms of its impact or broader benefits to society
Purpose: The programme or project purpose, which is also known as the specific objectives should address the core problem and be defined in terms of the intended direct benefits to the beneficiaries or target group
Outputs: also referred to as results, describes the product of the intervention which accords benefits to the target group
Activities: Activities describe how the programme or project is implemented, what it will do to produce the expected or desired output.

## Slide 62: Considering Assumptions
It is obvious that when objectives are set not all of them would have to be addressed by the programme or project.
As strategies are set and transposed into the PDM those that are left out, together with other external factors, are likely to affect the programme or project implementation and long term sustainability.
Assumptions describe the external environment of the programme or project and constitute factors that influence programme or project performance and sustainability but which are beyond the direct control of the programme or project.
They must be presented as positive conditions that need to be in place in order to move from activities through to the goals.

## Slide 63: Considering Assumptions…
This helps management to be constantly aware of the risks and uncertainties facing the programme or project
The relationship between the programme or project structure and the external environment is summarized in the “if and then” statement
For example, if the activities are carried out and certain assumptions hold true then outputs will be achieved

## Slide 64: Assumptions & Preconditions
Preconditions on the other hand are factors that must be met before commencement of the programme or project. ( ex. Employ professionals, secure funding, secure good will of the target groups, have legal status, etc).
These conditions need to be met if the programme or project is to succeed and for the benefits to become sustainable
They are therefore different from assumptions.
In adding assumptions into the PDM two steps need to be distinguished namely; identifying assumptions and assessing the assumptions

## Slide 65: Identifying Assumptions
From the objectives analysis, identify those objectives that are not considered within the selected strategy but which are important in determining the success of the programme or project.
Place them as factors that are beyond the control of the programme or project at the appropriate levels on the PDM.
Identify other external factors that must be fulfilled in order to achieve the overall goal, the programme or project purpose and the output.
Identify pre-conditions that have to be met before commencement of programme or project activities.

## Slide 66: Assessing the Assumptions
Assess the importance of the external factors based on conclusions arrived at after analyzing the following;
The external factor that answers almost uncertainly to the question if it will be realised, must be left out.
The external factor that answers likely should be included as an assumption.
The one that seem unlikely must be redesigned

## Slide 67: Ensuring Programme/Project Sustainability
Once the intervention logic has been established, and prior to completing the PDM it is important to ascertain that the sustainability of the intended programme/project benefits are analyzed.
Sustainability means the degree to which the benefits or long term impact of a programme or project are carried beyond the lifecycle and after all the input processes or the major part of donor assistance have been completed.
The PCM approach ensures that the sustainability factor is in-built in the design process rather than being hastily considered as an add-on concern at programme or project completion
A timely sustainability analysis will allow for additional outputs or activities to be included in the programme or project during the planning phase in order to increase the chances of sustaining the benefits

## Slide 68: Assess programme or project sustainability
The following factors need to be considered;
Ownership by beneficiaries:
Policy framework
Appropriate technology
Environmental issues
Socio-cultural issues
Gender balance
Institutional and management capacity

## Slide 69: Objectively Verifiable Indicators
SEE INDICATORS WHILE ADDRESSING M&E.
Objectively verifiable indicators define targets, which form the basis for performance measurement and the monitoring and evaluation system.
They describe the programme or project in operationally measurable terms
Once indicators have been identified they should be defined in terms of quantity, quality, time, target group and location to ensure that they are specific

## Slide 70: Objective: Standard of life improved
Set Quality (how better): Incidence of poverty reduced
Set target group (who): Incidence of poverty reduced among the youths
Set location (where): Incidence of poverty reduced among the youths in rural and sub-urban communities
Set quantity (how many or how much): Incidence of poverty reduced among the youths in rural and sub-urban communities by 30%
Set timeframe (when): ): Incidence of poverty reduced among the youths in rural and sub-urban communities by 30% within three years

## Slide 71: Objective: Standard of life improved…
Indicator 1: Incidence of poverty reduced among the youths in rural and sub-urban communities by 30% within three years.
Indicator 2: Increase the rate of self-employment and the creation of income generating activities by the youths in rural and sub-urban communities by 50% within three years.
Indicator 3: Reduce the rate of HIV/AIDS infection among the youths in rural and sub-urban communities from 40% to 20% by 2013

## Slide 72: Means of Verification
See it with M&E and show the table of p2p project
There must be a means by which to show evidence that your work has been done
The means of verification define the sources of information for verifying progress in achieving set targets.
This entails defining the process of data collection throughout the programme/project cycle.
Means of verification are the instruments providing information that makes it possible for indicators to be monitored and verified
When indicators are formulated, the source of information and means of collection should be specified

## Slide 73: How to Identify means and Costs
Means and costs refer to the human, material and financial resources needed to execute the programme or project
In order to provide an accurate estimate of the inputs for the programme or project, planned activities and management support activities must be specified in sufficient details.
The cost for collecting data on the indicators should be given high consideration

## Slide 74: Strengths and Weaknesses of the PDM
The LFA encourages people to consider expectations and how to achieve objectives
Checks the internal logic of the plan ensuring activities, outcomes and objectives are linked.
It forces planners to identify critical assumptions and risks affecting project success
Planners think about how to monitor and evaluate process and impact indicators
A powerful but not a comprehensive tool for planning or management
It is time consuming and requires a thorough understanding of the logic and of the concept of the logical framework analysis.
Problems can be compounded by too rigid application of the LF (changing environment)
LFA should be supported by technical, economic, social and environmental analysis
Strengths
Weaknesses

## Slide 75: Role of the Logframe in Monitoring, Evaluation & Reporting
The obvious sequence of events after programme or project planning and funding is implementation.
In the ideal six-phase programme or project cycle implementation occupies the fifth position.
It is during this phase that the actual work of the programme or project takes place.
Programmes and projects if they are implemented without sufficient controls will hardly go according to plan

## Slide 76: Differentiating between Monitoring and Evaluation
What is monitoring?
A systematic management activity
Analyses efficiency & effectiveness – measures actual against planned activities to identify remedial action
How is it done?
Rapid & continuous analysis, useful to improve on-going actions
Focuses on resources, activities & results in the logframe
Important in improving performance
Who does the monitoring?
Internally by staff but can also be done by external monitors
When is it done?
Regularly – on a day-to-day basis
Takes place at all levels of
What is Evaluation?
Systematic & objective assessment of a programme or project
Assesses the relevance, efficiency, effectiveness, impact & sustainability in relation to objectives
Focuses more on results-to-purpose & purpose-to-overall objectives
How is it done?
In-depth analysis,
Identify lessons learnt
Who does the evaluation?
Specialist external evaluators.
When is it done?
Periodic - once or twice during the programme or project cycle.
Monitoring
Evaluation

## Slide 77: Reporting
Programme and Project Managers will want to review progress very frequently, say monthly against contracted budgets and planned activities
A few selected items plus aggregated data on equipment and materials are considered key indicators for reporting on progress recorded
For monitoring to be described as complete and successful, information collected must be communicated – in the right form, to the right person and at the right time
This enables timely and appropriate management decision making

## Slide 78: Progress Reports
Progress reports are periodic summaries of progress made in the implementation of programme or project activities, incorporating key information from the physical and financial indicators
The report should cover the following areas;

## Slide 79: Progress Reports ….
Summary of the current status of the programme or project against indicators for programme or project purpose and outputs
Major activities undertaken during the reporting period as compared to the activity schedule
Programme or project expenditure for the reporting period as compared to the budget and cost schedule
Estimates of the number of clients and beneficiaries reached out to during the period
Current and anticipated problems and constraints encountered during the period and how they have been handled or planned to be handled
Planned major activities and schedules for the next period