## Slide 1: STRATEGIC CONSTRUCTION PROJECT MANAGEMENT “Without strategy the Organization is like a ship without a rudder “ Joel Rossand Michael kami.

## Slide 2
  1.1. Introduction: construction project & strategic management
1.2. Construction Project Planning Processes
1.2.1. Project planning at the initiation phase( project brief & charter, Feasibility study & Project proposal and Execution strategy)
1.2.2. Project planning at the design phase(Approval to go ahead with design and development Design product, develop detailed program: WBS, CPM, budget Baseline plan, design drawings and specifications)
1.2.3. Project planning at the executing/implementation phase (Approval to implement project, Solicit tender and award contracts, administer contracts, make the product/solve problem, Completed project output)
1.2.4. Project planning at the commission phase (Commissioning plan, notification of completion, Start-up and test the product, Produce as built drawings, compile knowledge learnt, Project closeout report)

## Slide 3: INTRODUCTION : CONSTRUCTION PROJECT
Construction projects are critiqued
  financial and managerial problems
  Not completed within schedule and budgeted cost….Dispute
Construction projects Exposed to uncertain environments: Construction complexity, presence of various interest groups( owner, end user, consultant, contractors, financers), material, equipment, project fund , climate environment….etc.
Construction project is a mission undertaken to create a unique facility, product or service with in scope, quality, time & cost

## Slide 4
Construction projects objectives:- completion of project with in time, budgeted cost, quality/specifications
Major project resource is cash….cash flow forecast should be prepared, managed and utilized well
Cash flow forecast: help to understand project cash demand with respect to time, the time when projects demand external financial support & plan where to get finance
Main actors of construction …contractors (low financial capacity)….finance projects from different source:
Internal:
  Depreciation allowance:
  Accounts payable:( Material,)
  Wage payable:
  Retained earnings: internal source of financing for expansion and growth
  Accruals፡ ( sub contracts, salaries, wages, taxes)

## Slide 5
External: involving third party like banks
  Term loan:
  Equipment loan
        Construction loan፡ Supplier’s Credit and Sub Contracting
          Overdraft facility: Unsecured overdraft facility/line of credit (usually one year , agreement b/n bank and the firm)
  Bridge financing

## Slide 6: Major Projects characteristics
Unique: innovative characteristics depending on the type of projects, Uncertainty & Changes
Temporary, for it has a definite beginning and ending constrained by finance
A component of a certain business or program, requiring predetermined goals and courses of actions; and hence Performance- Oriented and Constrained
Complex: size, variety, handling difficulty, importance, urgency, changes

## Slide 7: Construction projects have one or more of the following characteristics associated with them:
Time and cost is bounded
Details of works are not precisely defined.
Scope of work gets modified during execution
Nature of work varies from job to job
Place of works are spread out
Resource requirements and organization of works differ with each task
Investments involved are large and the decisions entail risks

## Slide 8: What is Strategy?
A strategy is a comprehensive action plan that identifies long-term direction and guides resource utilization to accomplish organizational goals with sustainable competitive advantage

## Slide 9: STRATEGIC MANAGEMENT
Is the art and science of formulating, implementing, and evaluating cross-functional decisions that enable the organization to achieve its objectives."
but covers cross-functional or overall organization.
comprises all such functional areas as marketing, finance & account, human resource, and production & operation into a top level management discipline.
Strategic management deals with organizational level and top level issues whereas:
functional or operational level management deals with the specific areas of the business.

## Slide 10: Cont.
Top-level managers such as Chairman, Managing Director, and corporate level planners involve more in strategic management process.
Strategic management relates to setting vision, mission, objectives, and strategies that can be the guideline to design functional strategies in other functional areas
Therefore, it is top-level management that paves the way for other functional or operational management in an organization.

## Slide 11: Cont.
A plan prepared well before the commencement of construction is instrumental in formulating directions, coordinating functions, setting targets, forecasting resources, budgeting costs, controlling performance and motivating people.

## Slide 12
Items, which need to be adequately planned, include:
The identification of specific activities of work.
The proper sequencing of the specific activities of work (precedence relationships)
time of delivery of materials and installed equipment.
types, quantities, and duration of construction plant and equipment
classification and numbers of workers needed and the periods of time they will be need
The amount and timing of financial assistance that is needed.

## Slide 13: Construction Project Planning Processes
planning process which, under normal circumstances, starts with the client providing the project’s terms of reference produces various plans to be used for the proper execution of the project.
major project inputs, processes and outputs of project planning in each phases of the project life time/ life cycle.

## Slide 14
Concept | Design | Implementation | Commission
Inputs |  |  | 
Problem, opportunity, project brief, project charter | Approval to go ahead with design and development | Approval to implement project | Commissioning plan, notification of completion
Processes |  |  | 
Feasibility study | Design product, develop detailed program: WBS, CPM, budget | Solicit tender and award contracts, administer contracts, make the product/solve problem | Start-up and test the product. produce as built drawings, compile knowledge learnt
Outputs |  |  | 
Feasibility study, Project proposal, Execution strategy | Baseline plan, design drawings and specifications | Completed project output | Project closeout report

## Slide 15: A. PROJECT PLANNING AT THE INITIATION PHASE
Aims at formulation of project scope and implementation strategy by project need identification, feasibility studies, investment appraisals, financial appraisal, statutory clearance, project definition; development of strategy for execution (project charter) and finally structuring of project organization including selection of the project manager (if project is approved for implementation).
End of initiation phase marks the client go-ahead/no-go decision.
The concept phase include:
Problem or opportunity, project brief, project charter
feasibility study
Project proposal and Execution strategy

## Slide 16: i Problem or opportunity, project brief, project charter
involves the process of formally recognizing a newproject exists
documented in the form of a project charter, also known as terms of reference (TOR) or project mission.
project charters are documents [usually supplied by clients] signifying the initiation of a project
A project charter is a tightly worded document outlining what is to be done and the boundaries of the project. For example, most part of charter from a client can be summarized as:
to build an 80,000 seat stadium in Addis, to Olympic standards, to be completed six months before the next CAF African Nation’s Cup tournament, for X Million birr.

## Slide 17
A project charter should generally include:
  Background to the project
  Key assumptions
  Business needs and other commercial needs
  Scope of work
  Identify key activities, budgets and milestones
  Comment on how the project is to be managed

## Slide 18: ii. Feasibility study
The important facets covered in project feasibility analysis
  Market analysis
  Technical analysis
  Financial analysis
  Economic analysis
  Ecological analysis

## Slide 19
Market Analysis: concerned primarily with aggregate demand and market share.
Technical Analysis: determine whether the prerequisites for the successful commissioning of the project have been considered and reasonably good choices have been made with respect to location, size, process, and so on.
Financial Analysis: ascertains proposed project will be financially viable(profitability or rate of return (ROR), cash flow, and pay-back of investment): able to meet the burden of servicing debt and satisfy the return expectations of those who provide the capital.

## Slide 20
Net present value of cash flow (NPV),
Internal rate of return (ROR),
Pay-back period (PBP),
Simple rate of return (SRR),
Break-even point (BEP), and
Sensitivity analysis (SA).

## Slide 21
Economic Analysis: refers to cost benefit analysis which may often be different from its monetary costs and benefits.
Ecological Analysis: It is particularly required for major projects which have significant ecological implications like power plants and irrigation schemes, and environmental-polluting industries.

## Slide 22: iii. Project proposal and Execution strategy
Information generally contained are as follows:
  Project background and description,
  Market and plant capacity,
  Materials and input,
  Location and sites,
  Project engineering and investment cost,
  Plant organization and overhead cost, Manpower,
  Implementation schedule, and Financial and economic evaluation.

## Slide 23: PROJECT PLANNING AT THE DESIGN PHASE
Approval to go ahead with design and development
Design product, develop detailed program: WBS, CPM, budget
Baseline plan, design drawings and specifications

## Slide 24: Approval to go ahead with design and development
The feasibility report, if found acceptable, is followed up with investment appraisal. The purpose of appraisal is to conduct an objective assessment for investment decision. Appraisal of feasibility stage enables a client to:
decide on the project concept, time and costs;
outline the approach needed to taking the project;
appoint key persons like construction project manager or project coordinator, to act as his representatives;
nominate specialist associated agencies such as the architect, designer and consultants, as per requirements.

## Slide 25: ii. Design product, develop detailed program
Planning and design phase covers the following:
Basic designs and drawings planning,
Time planning,
Cost planning and budgeting,
Communications planning,
Quality planning,
Organisational planning,
Risk management planning,
Procurement planning, and
Project development integrated plan.

## Slide 26: iii. Baseline plan, design drawings and specifications
Design, drawings and specifications define the construction scope of the project.
Design forms the base for determining the functional fitness of the proposed facility
development of the drawings, estimation of cost of the project and the quantity of work, deciding construction time and forecasting cash-flow.
During design process, project information collected, analysed, communicated and recorded for incorporation into the proposed scope of work.

## Slide 27
Designing follows three sequential processes
1.Schematic Design Process: In the project feasibility stage, the designer architect evaluates the client's requirements. After discussing the alternatives with the client, the designer then prepares conceptual design brief for the client's approval,
2. Design Development Process: This phase commences after approval of schematic designs. The emphasis in this phase shifts to details of constructability, system integration and aesthetics. Drawings in this phase include plan, elevation and section of the facility & external services.
3. Drawings and Specifications Documentation Processes: This process includes preparation of the construction drawings and specifications based on approved designs. The construction drawings and specifications form part of the contracted bids.

## Slide 28: C.PROJECT PLANNING AT THE EXECUTING/IMPLEMENTATION PHASE
Approval to implement project
Solicit tender and award contracts, administer contracts, make the product/solve problem
Completed project output

## Slide 29: i. Approval to implement project
At this stage all the construction or contract documents are finalized
contract documents are communication link among all parties in the project ,divided into three general sections
  bidding,
  contractual, and
  technical
The bid requirements, agreement, technical specifications, drawings, addenda, and contract modifications all form part of the construction document.

## Slide 30: Solicit tender and award contracts, administer contracts, make the product/solve problem
major activities undertaken at this stage are:
1. Tendering: contractors are invited to offer their best technical and financial offers as per the conditions of contract and specifications depicted in the tender documents.
2. Award of Contract
After the negotiations have been successful, the contract will be awarded to the most responsible bidder.
3. Procurement of Materials: procure the required materials at site.
4. Construction and Supervision: Construction and supervision both are complementary to each other.
  Execution involves establishing direction, communicating vision, motivating and inspiring people to produce desired results.
  Leadership is not, limited to the project manager. Leadership must be demonstrated at all levels of the project (project leadership, technical leadership, team leadership).

## Slide 31: Project Control
Project Control follows system concept:
  Overall scope change control
  Resource control
  Schedule control
  Cost control
  Quality control
  Risk response control
  Performance reporting

## Slide 32
Each organizational unit in a project, usually referred as Responsibility Centre, can be viewed as a sub-system.
These sub-systems are highly interdependent and interactive.
The performance objectives of sub-systems are stated in terms of parameters to be controlled, these parameters include time progress targets, resources productivity standards and work package standard costs and sales targets.
Each sub-system accounts for its performance and reports the actual, and the deviation between the planned and the actual performance, to the monitor.

## Slide 33: iii, Completed project output
Project close up includes the following tasks:
  Administrative Close,
  Contract Closeout, and
  Lessons Learnt.

## Slide 34
For proper closing of project:
The post-completion maintenance is usually entrusted to an agency familiar with the construction. In most cases, the contractor responsible for construction is given this responsibility for one year after completion
A proper record of the operating instructions and as-built drawings is maintained.
The staff and workers necessary for operating and maintaining the facility are trained prior to its taking over.
The site is cleared of the left-outs of the construction and unwanted materials.
The client fully safeguards his interests prior to rending the completion certificate to the contractor, and also before making the final payments.

## Slide 35
After completion by the contractor, it is the project team of the client that hands over the project to him. The team also prepares a project completion report which includes:
the scope and schedule of work
the important events
the contract executed
the addresses of the suppliers of materials and equipment
the equipment maintenance manual
the as-built drawings
the costs involved
the problems encountered during execution
the lessons learned &
the minor defects noticed at the time of handing over

## Slide 36: D. Project Planning at the Commission Phase
project planning Outputs in construction projects include:
Commissioning plan, notification of completion
Start-up and test the product, Produce as built drawings, compile knowledge learnt
Project closeout report

## Slide 37
This is a significant event for both the owner and the contractor:
The acceptance of a completed project is customarily based on a final inspection performed by the owner’s representative and conditioned upon the correction of any deficiencies noted.
If the facility or a portion thereof is substantially complete, the owner’s representative will execute a certificate of substantial completion for the work. The contractor may then require and receive a final progress payment. However, sufficient retain age is withhold to ensure the correction of any remaining deficiencies.

## Slide 38
Final payment and its acceptance by the contractor usually constitute a waiver of all claims by either the owner or contractor except for unsettled liens and claims and deficiencies falling under warranty provisions.
In most, if not all, construction projects the major processes under this stage are two: Commissioning and Acceptance.
Notes: lien /· n. Law a right to keep possession of property belonging to another person until a debt owed by that person is discharged.

## Slide 39: Commissioning
Commissioning is a process whereby the contractor makes sure that all installed electro – mechanical and other parts are operational or functional.

## Slide 40: Acceptances
it includes:
Provisional Acceptance: - This is avoids of acceptance the completed work on provisional basis for a period of one year.
Final Acceptance:-At this stage the owner completely accepts the works executed in total and the retention money is released to the contractor.

## Slide 41: Changes and delays
The document directing a change is referred to as a change order.
The majority of changes are due to design modifications initiated by the owner or designer
All change orders issued should contain an adjustment in contract time and price which is mutually acceptable to the contractor and owner.
The three general categories of delay include those beyond the control of either the contractor or the owner “acts of God”, those under the control of the owner, and those under the control of the contractor.

## Slide 42
2.1 INTRODUCTION
2.2 WHAT IS STRATEGIC PLANNING
2.3 IMPORTANCE OF STRATEGIC PLAN
2.4 FORMULATION OF STRATEGIC PLAN
CHAPTER 2፡ STRATEGIC PLANNING

## Slide 43: 2.1 INTRODUCTION
Good project management methodologies allow work to be accomplished in less time, at lower cost, with fewer resources, and without any sacrifice in quality.
Strategic planning is vital for every project.
Effective strategic planning can mean the difference between long-term success and failure.
Strategic planning for excellence in project management needs to consider all aspects of the company: from the working relationships among employees and managers and between staff and to the company’s corporate structure and culture.

## Slide 44: 2.2 WHAT IS STRATEGIC PLANNING?
Simply put, a strategic plan is the formal­ized road map that describes how your organization executes the chosen strategy.
A plan spells out where an organization is going over the next year or more and how it is going to get there. A strategic plan is a management tool that serves the purpose of helping an organization do a better job, and it improves organizations because a plan focuses the energy, resources, and time of everyone in the organization in the same direction.

## Slide 45: 2.2, WHAT IS STRATEGIC PLANNING
It is the process of formulating decisions about an organization’s future direction.
it is the process by which the organization adapts to its ever-changing environment.
And the process is applicable to all management levels and all types of organizations
Strategic planning for project management is the development of a standard methodology that can be used for achieving the project’s objectives.
Without this process, subunits tend to drift off in their own direction without regard to their role as a subsystem in a project.

## Slide 46: 2.3, IMPORTANCE OF STRATEGIC PLAN
Strategic project plan serves as a vehicle for the communication of project objectives to all levels of management in an organization and gives all levels an opportunity to participate.
It affords the potential of a vertical feedback loop from top to bottom, bottom to top, and functional unit to functional unit.
Benefits of a written plan
A written plan will Form the basis for decisions on allocation of resources (financial and human)
A written plan is an important tool to guide the activities of a project.
A written plan will help to ensure that everyone is working towards the same ideals for the future so it is important to spend some time reflecting on and defining the objectives of a project.

## Slide 47: 2.4. FORMULATION OF STRATEGIC PLAN
Formulation of a strategic plan is performed at the top levels of the organization. (Formulating Strategies)
Formulation process of Strategic plan is the process of deciding where you want to go, what decisions must be made, and when they must be made in order to get there.
outcome of successful formulation results in the organization doing the right thing in the right way (i.e., it results in project management) by producing goods or services for which there is a demand or need in the external or internal environment.

## Slide 48: 8 steps to developing a strategic plan
STEP 1. Prepare to plan
STEP 2. Identification of a project’s vision mission goals and project goals
STEP 3. Analyze the internal and external environment
STEP 4. Identify the strategic issues
STEP 5. Define the strategic aims
STEP 6. Identify the resources required to achieve the strategic aims
STEP 7. Draw up an internal capacity building plan
STEP 8. Cost the plan

## Slide 49: STEP 1: PREPARING TO PLAN
This step builds consensus around some of the questions:
Who will be involved in the process?
What will their precise roles be?
Who will be involved from outside the organization?
What kind of external perspectives and experiences will help in planning?
How much time will be set aside for strategic planning? And over what period of time?
How much time will different members of the team allocate to strategic planning?
What is the timetable?
Who will be responsible for collecting the relevant documents? (Planning will be quicker and easier if relevant documents are collected in advance)

## Slide 50
The time an organization invests in preparing to plan can yield huge dividends in the quality of the final product, so preparation deserves dedicated time and careful thought.
some tips for successful strategic planning.
Make a list of who might be involved in the process
Consider what particular skills and experience each person can bring to the process.
Allocate precise tasks to individuals in a work plan and timetable.
Agree on what external inputs you might need for different parts of the process and invite the relevant people.

## Slide 51
No. | Members Name | Skills & experience | external inputs | external perspectives and experiences
1. |  |  |  | 
2. |  |  |  | 
No. | Members Name | Tasks |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Time table |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 52: STEP 2: IDENTIFICATION OF A PROJECT’S VISION AND MISSION: PROJECT GOALS
Mission Statement:-A projects mission statement describes its reason for existence in general terms that capture its unique purpose and functions. It typically describes the organization, what it does, why it does it, and for whom.
Vision Statement:- The vision statement is a brief, forceful statement describing the project at its most effective, or as it will be when it achieves its desired goals and outcomes.
Vision examples:
Great people, great service, excellence every time.
The department is recognized as a progressive, innovative leader as we promote economic vitality, safeguard the environment, provide world-class customer service and embrace change.

## Slide 53
Goals: Goals are broad, high-level, issue-oriented statements of outcomes that an organization will strive to achieve. They should fit well with the mission statement and values, and answer the question, "What must we do to accomplish our mission or achieve a result?"
Objectives: Objectives break down goals into smaller, more specific pieces. They describe measurable results a project expects to accomplish within a given time period.
  A good objective statement will provide an operational way to know if your strategies are successfully moving toward your goal. Try to start each objective sentence with one of these words: increase, decrease, or maintain.

## Slide 54: STEP 3: INTERNAL AND EXTERNAL ENVIRONMENT ANALYSIS
Assessment of external challenges and opportunities external factors that affect the ability to achieve goals and performance targets.
Related markets or industries
The law or regulatory environment
The natural environment
2.Assessment of internal capacity and financial health organization to take stock of its strengths and weaknesses, and to examine internal organizational factors that can impact its ability to accomplish the mission, goals, and objectives.
For example:
What are key workforce issues that affect projects performance?
What workforce issues must be addressed to achieve project goals?
Will your strategies require an increase in staff and, thus, a need for more space?
What technology will be necessary (and in what time frame) to achieve goals?

## Slide 55
some key questions to guide internal environment analysis.
What human and financial resources and capacity are available?
What are the organization’s weaknesses and strengths?
Identifying the human and financial resources and capacity available to the project means looking at:
The skills, experience, knowledge and expertise of current staff as well as their roles and responsibilities
Overall income trends, including present and projected financial resources.
Analyzing strengths, weaknesses, opportunities and constraints

## Slide 56: SWOT (Strengths, Weaknesses, Opportunities, and Threats)
Under SWOT analysis, an organization explicitly identifies external and internal environment in which an organization is operating:
internal factors (strengths and weaknesses)
external factors (opportunities and threats) that may impact its ability to achieve results.

## Slide 57: QUIZ(10%)
Write 8 steps to developing a strategic plan implementation process
Define the following terms:
Strategic Planning
SWOT analysis
3)List out the Importance Of Strategic
4) Discourse briefly What you have learned

## Slide 58: Assessment Model :S W O T
External Assessment: Marketplace, competitor’s, social trends, technology, regulatory environment, economic cycles .
Internal Assessment: Organizational assets, resources, people, culture, systems, partnerships, suppliers, . . .
Easy to Understand
Apply at any organizational level
Needs to be Analytical and Specific
Be honest about your weaknesses
Good Points
Possible Pitfalls
SWOT
SWOT

## Slide 59: Strength’s
Strength’s – Those things that you do well, the high value or performance points
Strengths can be tangible: Loyal customers, efficient distribution channels, very high quality products, excellent financial condition
Strengths can be intangible: Good leadership, strategic insights, customer intelligence, solid reputation, high skilled workforce
Often considered “Core Competencies” – Best leverage points for growth without draining your resources

## Slide 60: Weaknesses
Weaknesses – Those things that prevent you from doing what you really need to do
Since weaknesses are internal, they are within
your control
Weaknesses include: Bad leadership, unskilled
workforce, insufficient resources, poor product
quality, slow distribution and delivery channels,
outdated technologies, lack of planning, . . .

## Slide 61: Opportunities
Opportunities – Potential areas for growth and
higher performance
External in nature – marketplace, unhappy
customers with competitor’s, better economic
conditions, more open trading policies, . .
Internal opportunities should be classified as
Strength’s
Timing may be important for capitalizing on
opportunities

## Slide 62: Threats
Threats – Challenges confronting the organization,
external in nature
Threats can take a wide range – bad press
coverage, shifts in consumer behavior, substitute
products, new regulations, . . .
May be useful to classify or assign probabilities to
threats
The more accurate you are in identifying threats,
the better position you are for dealing with the
“sudden ripples” of change

## Slide 64: SWOT results
After completing your SWOT analysis, a best practice is to address the following challenges:
  How can the organizational sustain the strengths identified
  How might the organization use strengths to take advantage of opportunities identified and overcome threats
  How can the organization minimize or overcome weaknesses in order to take advantage of opportunities and overcome threats
One of the best ways to address these challenges and translate the findings into useful material for later in the strategic planning process is to develop a modified SWOT matrix:
 | Strengths | Weaknesses
Opportunities | S-O strategies | W-O strategies
Threats | S-T strategies | W-T strategies

## Slide 65
S-O strategies pursue opportunities that are a good fit our strengths.
W-O strategies overcome weaknesses to pursue opportunities.
S-T strategies identify ways that we can use its strengths to reduce our vulnerability to external threats.
W-T strategies establish a defensive plan to prevent our weaknesses from making us highly susceptible to external threats.

## Slide 66: STEP 4: IDENTIFYING STRATEGIC ISSUES
It is designed to help answer the question: What are the key strategic issues that the organization wants to address? It is important to identify the strategic issues that have emerged from the analysis so far because this helps to:
To Focus attention on really important issues
To Identify the major choices facing the organization
To Highlight areas needing change
To Provide insights about how to resolve the issues.

## Slide 67: What are strategic issues?
Strategic issues are best stated and written down as questions because this will help highlight areas where the organization needs to make choices and decisions.
They may relate either to the aims of the organization, or to its mandate, or to the analysis of the external and internal Environment and the results of the SWOT analysis.
They will thus comprise a combination of program and organizational capacity issues.

## Slide 68
To test whether or not an issue is really strategic, examine each issue in terms of the questions below.
Is it possible to explain why it is a burning issue?
Can the organization do anything about the issue?
Does the issue have significant implications for financial or human resources?
Will there be negative consequences if this issue is NOT addressed?
If the answer to most of these questions is ‘yes’, it is likely that the issue is strategic.
It is likely that many strategic issues will remain on the list even after those which fail this test have been eliminated.
The next step is to prioritize the remaining strategic issues, group them and synthesize them into strategic aims.

## Slide 69: STEP 5: DEFINING STRATEGIC AIMS & DEVELOP STRATEGIES
The key questions to ask in this step are:
What are the strategic aims of a project?
Which strategic aims should be prioritized?
1. What is a strategic aim?
A strategic aim states clearly and precisely what the organization wants to achieve from the project during this time and how it intends to achieve it.
2. What are strategies?
Strategies are statements of methods to achieve objective.
While goals and objectives state what the organization wants to achieve,
strategies state how goals and objectives will be achieved
Strategies are the paths that the organization will follow as it works towards achieving the identified strategic aims.

## Slide 70: STEP 6: IDENTIFYING RESOURCE NEEDS
what human and financial resources will be needed to achieve the aims of the strategic plan.
Through this step it is needed to answer the following questions
What financial resources are currently available, for which aspects of the work planned?
What human resources are currently available for the project (analyze staff skills and experiences)?
What are the gaps between what is available and what is needed?
How might these gaps best be filled? For example, consider the merits of staff development and training, the employment of new staff.
This analysis will provide the basis of both the internal capacity building plan and the costing of the strategic plan.

## Slide 71: STEP 7: INTERNAL CAPACITY BUILDING PLAN
Number of strategic issues will have been identified that relate organizational capacity, its strengths or weaknesses directly to the final strategic aims, it is important to link them to the strategies for achieving those aims.
However, some issues will be broader and are best addressed by developing an internal capacity building plan. This will help to ensure that the organization successfully builds on the strengths it has identified and minimizes or overcomes its weaknesses.
The internal capacity building plan should specify what areas of capacity need to be addressed and how they will be addressed.

## Slide 72: STEP 8: COSTING THE STRATEGIC PLAN
concerns the resources that will be needed to implement the strategic plan.
In other words it will need to cover the strategies identified for each Strategic aim and the internal capacity building plan.
At this stage it is sufficient to have an estimate of project costs.
COSTING: factors to consider when costing.
Identify the inputs: - required to implement each strategy in terms of people, equipment, services and materials.
Categorize the costs of inputs: - One way of doing this is to distinguish between indirect and direct costs

## Slide 73
Introduction
Plans, program, and projects
Strategic implementation process
Resource allocation
Designing organization structure
Implementing strategic change
Chapter 3: Strategic Implementation

## Slide 74: Introduction
Translation of strategic thought in to strategic action. Translation requires support of managers and employees of the organization.
Strategy implementation is "the process of allocating resources to support the chosen strategies".
strategy implementation includes
    designing the organization's structure,
    allocating resources
    developing strategic control systems.
    To implement the strategic plan successfully, it is necessary for the organization to have a formal implementation plan with actions assigned to either teams or individuals who are responsible for their accomplishment.

## Slide 75
Implementation process can also be thought of as having several parts:
Resource planning and the logistics of implementation. The process will address the problems of tasks that need to be carried out and also the timing of them. There may need to be change in the mix of resources required to implement the strategy and decision will need to be taken about who is to be responsible for the change.
The organizational structure may need to be changed. E. g from hierarchical to matrix or from centralized to decentralize.
The systems employed to manage the organization may be changed or improved. The systems provide information and operational procedures needed in the organization.
It may be that a new information management system is required to control the progress of the strategy. Staff may need to be retrained or new staff recruited.

## Slide 76: Strategy formulation & implementation contrasted :
STRATEGY FORMULATION | STRATEGY IMPLEMENTATION
Strategy formulation is positioning forces before the action. | Strategy implementation is managing forces during the action.
Strategy formulation focuses on effectiveness. | Strategy implementation focuses on efficiency.
Strategy formulation is primarily an intellectual process. | Strategy implementation is primarily an operational process.
Strategy formulation requires good intuitive and analytical skills. | Strategy implementation requires special motivation and leadership skills
Strategy formulation requires coordination among a few individuals | Strategy implementation requires combination among many individuals.

## Slide 77: Basic Purpose of Management
EFFICIENTLY Using resources wisely and in a cost-effective way
EFFECTIVELY Making the right decisions and successfully implementing them
And
Notes: 6

## Slide 78: PLANS, PROGRAMMES, AND PROJECTS
The strategic plan devised by the organization proposes the manner in which the strategies could be put into action.
Programme is a broad term, which includes goals, policies, procedures, rules, and steps to be taken in putting a plan into action. Programs are usually supported by funds allocated for plan implementation.
project is a highly specific Programme for which the time schedule and costs are predetermined. It requires allocation of funds based on capital budgeting by organizations.

## Slide 79: Strategic Implementation Process
There are five-stage model of the strategy implementation process:
Determining how much the organization will have to change in order to implement the strategy under consideration.
Analyzing the formal and informal structures of the organization.
Analyzing the "culture" of the organization.
Selecting an appropriate approach to implementing the strategy.
Implementing the strategy and evaluating the results.

## Slide 80: RESOURCE ALLOCATION
The resources may be existing with a company or many be acquired through capital allocation.
Resources include: physical, financial and human resources essential for implementing plans.
Resources are broadly of four categories.
Money
Facilities and equipment's
Materials, supplies and services
Personnel

## Slide 81: DESIGNING ORGANIZATION STRUCTURE
organizational structure is the pattern or arrangement of jobs and groups of jobs within an organization.
Organizational Design is the process of creating or reshaping an organizational structure optimized to support strategic decisions.
The elements of organization structure and design are:
Division of labor
Departmentalization-
Delegation of authority
Span of control

## Slide 82: IMPLEMENTING STRATEGIC CHANGE
Change occurs at three levels:
i) Individual level
ii) Group level and
iii) Organization level
The major types of strategic change are: re-engineering, restructuring, and innovation
Re-engineering: Business Process Re-engineering (BPR).
It is fundamental rethinking and radical redesign of business process to achieve dramatic improvements in critical, contemporary measures of performance such as cost, quality, service and speed. The strategist must completely think how the organization goes about its business. Instead of focusing on company’s functions strategic managers make business process the focus of attention.

## Slide 83
Restructuring: It is the second form of change to improve the firm’s performance. There are two basic steps to restructuring. First, an organization reduces its level of differentiation and integration by eliminating divisions, departments or levels in the hierarchy. Second, an organization downsizes by reducing the number of its employees to reduce operating cost.
Innovation: It is the process by which organizations use their skills and resources to create new technologies or goods and services so they can change and better respond to the needs of their customer. Innovation can be done with the help of research and development department.

## Slide 84: Stages in the strategic Change Process

## Slide 85
Determine the need for change:
In this step the strategic managers must recognize a gap between actual performance and desired performance, use a SWOT analysis to define the company’s present state and then determine its desired future state.
Determine the obstacles to change:
Obstacles may prevent a company from reaching its desired future state. Conflict is also major setback to change and managers must seek ways to resolve the conflict to implement strategic change successfully.
Implement change:
Strategic managers play organizational politics to overcome obstacles to change, resolve conflicts and bring about strategic change. To play politics, managers must have power.
Evaluate change:
Strategic managers need to evaluate the results of each change process and use this analysis to define the organization’s present condition so that they can start the next change process.

## Slide 86: Chapter 4 Evaluation of the Strategy

## Slide 87
Organizations are most vulnerable when they are at the peak of their success
Erroneous strategic decisions can inflict severe penalties and can be exceedingly difficult, if not impossible, to reverse.
Strategy evaluation is vital to an organization’s well-being; timely evaluations can alert management to problems or potential problems before a situation becomes critical.
Strategy Evaluation

## Slide 88
Examine the underlying bases of a firm’s strategy
Compare expected to actual results
Identify corrective actions to ensure that performance conforms to plans
Strategy Review, Evaluation, & Control
3 Basic Activities

## Slide 89
Complex & sensitive undertaking
Overemphasis can be costly & counterproductive
No evaluation can create even worse problems.
Strategy evaluation is essential to ensure that stated objectives are being achieved.
Strategy Review, Evaluation, & Control
Strategy Evaluation

## Slide 90: Strategy Review, Evaluation, & Control
Have assets increased
Increase in profitability
Increase in sales
Increase in productivity
Increased Profit margins
Some ways to evaluate of Strategic Performance

## Slide 91: Strategy Review, Evaluation, & Control
Increase in environment’s complexity
Difficulty predicting future with accuracy
Increasing number of variables
Difficulties in Strategy Evaluation
Rate of obsolescence of plans
Domestic and global events
Decreasing time span for planning certainty

## Slide 92: Strategy Review, Evaluation, & Control
Initiate managerial questioning of evaluation and assumptions
Trigger review of objectives & values
Stimulate creativity in generating alternatives
Managers and employees of the firm should continually be aware of progress being made toward achieving the firm’s objectives. As critical success factors change, organizational members should be involved in determining appropriate corrective actions.
Strategy Evaluation Should --

## Slide 93: Strategy Review, Evaluation, & Control
Are strengths still strengths?
Have we added additional strengths?
Are weaknesses still weaknesses?
Have we developed other weaknesses?
Monitor Strengths & Weaknesses; Opportunities & Threats

## Slide 94: Strategy Review, Evaluation, & Control
Are opportunities still opportunities?
Other opportunities develop?
Are threats still threats
Other threats emerged?
Are we vulnerable to hostile takeover?
Monitor Strengths & Weaknesses; Opportunities & Threats

## Slide 95
Evaluation Framework
I. Review Underlying Bases
Continue present course
II. Measure Firm Performance
III.
Take
Corrective
Actions
Differences?
Differences?
Yes
NO
Yes
NO

## Slide 96: Strategy Review, Evaluation, & Control
Compare expected to actual results
Investigate deviations from plan
Evaluate individual performance
Progress toward stated objectives
Failure to make satisfactory progress signals a need for corrective action.
Measuring Organizational Performance: based on an long term and annual objectives

## Slide 97: Strategy Review, Evaluation, & Control
Financial Ratios
  Compare performance over different periods
  Compare performance to competitors
  Compare performance to industry averages
Quantitative Criteria for Strategy Evaluation

## Slide 98: Strategy Review, Evaluation, & Control
Return on investment (ROI)
Return on equity (ROE)
Profit margin
Market Share
Key Financial Ratios
Debt to equity
Earnings per share (EPS)
Sales growth
Asset growth

## Slide 99: Strategy Review, Evaluation, & Control
Taking corrective action, requires making changes to reposition a firm competitively for the future.
Examples of changes that may be needed are altering an organization’s structure, replacing one or more key individuals, selling a division, or revising a business mission.
Taking corrective action raises employees’ and managers’ anxieties. Research suggests that participation in strategy-evaluation activities is one of the best ways to overcome individuals’ resistance to change.
Taking Corrective action:

## Slide 100: Strategy Review, Evaluation, & Control
Strategy-evaluation activities must be economical; too much information can be just as bad as too little information.
Strategy-evaluation activities should also be meaningful; they should specifically relate to a firm’s objectives.
Strategy-evaluation activities should provide timely information; on occasion and in some areas, managers may need information daily.
Strategy evaluation should be designed to provide a true picture of what is happening.
CHARACTERISTICS OF AN EFFECTIVE EVALUATION SYSTEM

## Slide 101: Strategy Review, Evaluation, & Control
Return on investment (ROI)
Return on equity (ROE)
Profit margin
Market Share
Key Financial Ratios
Debt to equity
Earnings per share (EPS)
Sales growth
Asset growth

## Slide 102: Strategy Review, Evaluation, & Control
Currently process is more an “art” than “science”
Should strategies be visible or hidden from stakeholders
  Visible: Participation and openness enhances understanding, commitment, and communication within the firm.
  Hidden: Secrecy limits rival firms from imitating or duplicating the firm’s strategies and undermining the firm.
Should process be more top-down or bottom up
  Top executives are the only persons in the firm with the collective experience…; to make key strategy decisions.
  Lower- and middle-level managers and employees who will be implementing the strategies need to be actively involved in the process of formulating the strategies to assure their support and commitment.
21st Century Challenges in strategic Management