## Slide 1: Chapter-Three
Stake holder’s responsibility in construction projects

## Slide 2: Introduction
Definition
  Stake holder’s can be defined as either individuals or units or the organization itself for which they claim a stake in the project such that they get benefit from or affected by the whole processes of the project and its deliverables.
  In the construction context then, they are parties who will be interested in projects undertaken or products delivered by the industry.

## Slide 3: Major stakeholders in const. project
The major stakeholders of the construction industry are the client who finance the projects, the contractors who implement the projects, the consultants who design and supervise the works, and the regulators who regulate how the industry and its actions functions.
Client/Employer: are the parties (public or private) under who finance the project is executed
    Comes up with the investment needs such as project idea, land, capital etc.
    Responsible for Project Scope Definition; Project Financing; Administration (Limited); Organization and Risk allocations
    Usually provides the infrastructure needed
    Takes care of some of the legal constraints & permits

## Slide 4: Employer’s Responsibilities
Right of Access to the Site
  The Employer shall give the Contractor right of access to, and possession of, all parts of the Site within the time (or times) stated in the Contract Data.
Permits, Licenses or Approvals
  The Employer shall provide, at the request of the Contractor, such reasonable assistance as to allow the Contractor to obtain properly
      copies of the Laws of the Country which are relevant to the Contract but are not readily available, and
      any permits, licenses or approvals required by the Laws of the Country
      (2.3 )Employer’s Personnel and (2.4 )Employer’s Financial Arrangements
Refer FIDIC 1999/ harmonized FIDIC

## Slide 5: Client/Employer
In Ethiopian context, the major public clients in the construction industry include ;
  The Integrated Urban Housing Development Program Office (IUHDPO) under MoWUD,
  The Ethiopian Road Authority (ERA),
  The Ethiopian Electric Power Corporation (EEPCO),
  The Ministry of Water Resources (MoWR),
  The Defense Force, Ministry of Health, Ministry of Education, etc and their regional subsidiaries/equivalents.
  Besides, the private sector also takes a huge stake as a client, particularly in the housing sector.

## Slide 6: Consultant/Engineer
Consultants: are professional bodies who design the project
    Change the clients project idea into economic and constructible artifact
    Make sure that design satisfies requirements
    [Usually] prepare BoQ and contract documents
If assigned to supervise:
        Look after proper execution of project
        Administer the contract
        Certify payment certificates
        Issue provisional and final acceptance certificate etc.

## Slide 7: Engineer and Engineer’s Representative
Definition
  “Engineer” means the person appointed by the Employer to act as Engineer for the purposes of the Contract whose duties and autorities are listed below.
Engineer’s Duties and Authority
  The Engineer shall carry out the duties specified in the Contract.
  The Engineer may exercise the authority specified in or necessarily to be implied from the Contract, provided, however, that if the Engineer is required, under, the terms of his appointment by the Employer, to obtain the specific approval of the Employer before exercising any such authority, particulars of such requirements shall be set out in Part II of these Conditions. Provided further that any requisite approval shall be deemed to have been given by the Employer for any such authority exercised by the Engineer.
  Except as expressly stated in the Contract, the Engineer shall have no authority to relieve the Contractor of any of his obligations under the Contract.

## Slide 8: Engineer and Engineer’s Representative
“Engineer’s Representative” means a person appointed from time to time by the Engineer under Sub-Clause 2.2
Sub-Clause 2.2(Engineer’s Representative2.2)
  The Engineer’s Representative shall be appointed by and be responsible to the Engineer and shall carry out such duties and exercise such authority as may be delegated to him by the Engineer under Sub-Clause 2.3

## Slide 9: Engineer and Engineer’s Representative
Engineer’s Authority to Delegate his representatives
The Engineer may from time to time delegate to the Engineer’s Representative any of the duties and authorities vested in the Engineer and he may at any time revoke such delegation. Any such delegation or revocation shall be in writing and shall not take effect until a copy thereof has been delivered to the Employer and the Contractor.
Any communication given by the Engineer’s Representative to the Contractor in accordance with such delegation shall have the same effect as though it had been given by the Engineer.
Provided that:
    any failure of the Engineer’s Representative to disapprove any work, materials or Plant shall not prejudice the authority of the Engineer to disapprove such work, materials or Plant and to give instructions for the rectification thereof, and

## Slide 10: ….Continued
    if the Contractor questions any communication of the Engineer’s Representative he may refer the matter to the Engineer who shall confirm, reverse or vary the contents of such communication.
The Engineer or the Engineer’s Representative may appoint any number of persons to assist the Engineer's Representative in the carrying out of his duties under Sub-Clause 2.2.

## Slide 11: Engineer and Engineer’s Representative
Engineer to Act Impartially
Wherever, under the Contract, the Engineer is required to exercise his discretion by:
giving his decision, opinion or consent,
expressing his satisfaction or approval,
determining value, or
otherwise taking action which may affect the rights and obligations of the Employer or the Contractor
he shall exercise such discretion impartially within the terms
of the Contract and having regard to all the circumstances.
Any such decision, opinion, consent, expression of
satisfaction, or approval, determination of value or action
may be opened up, reviewed or revised as provided in Clause
67(Settlement of Disputes).

## Slide 12: Engineer and Engineer’s Representative
In general the main responsibility of the resident engineer
(RE) include, among other things;
To check and certify the contractors work program
To certify the contractors method of carrying out the works
To check that the works comply with the drawings
To see that the requirements of the specifications in regard to materials and workmanship are adhered to
To watch for faulty materials and workmanship
To issue further instructions and clarifications if necessary
To measure the amount of work done for payment purposes
To keep a record of all works measurement
To periodically report to the owner the progress of the works.

## Slide 13: Contractor
Contactors: are the parties that change the drawings and specification made by the consultants into a physical structure( “construction is physical realization of design”)
    Prepares a bid document
    Provides the resources needed to execute the project
    Executes the project according to the specification and legal requirements
    Monitors project execution
    Rectifies defects

## Slide 14: Contractor’s General Responsibilities
Under general obligation sub clause 8.1;
The Contractor shall, with due care and diligence, design (to the extent
provided for by the Contract), execute and complete the Works and
remedy any defects therein in accordance with the provisions of the
Contract. The Contractor shall provide all superintendence, labour,
materials, Plant, Contractor’s Equipment and all other things, whether
of a temporary or permanent nature, required in and for such design,
execution, completion and remedying of any defects, so far as the
necessity for providing the same is specified in or is reasonably to be
inferred from the Contract.
The Contractor shall give prompt notice to the Engineer, with a copy to
the Employer, of any error, omission, fault or other defect in the design
of or Specification for the Works which he discovers when reviewing
the Contract or executing the Works.

## Slide 15: Contractor’s General Responsibilities
The contractor’s right
Within the exercise of the construction activities the contractor has rights and obligations that are specifically indicated in the contract documents. The inspector must therefore consider these rights of the contractor whenever involvement in site inspection is necessary.
Such an action would necessitate the careful understanding and observance of the stipulations of the contract documents, including pre tender, tender documents, pre tender site visits minutes of meetings, memorandums of understanding signed during tender negotiations time, pre construction job site conference minutes, drawings, specifications, bill of quantities, addendum, soil investigation reports, standards specified in the contracts etc.

## Slide 16: Statutory bodies
Statutory bodies: are government bodies that looks after the project’s compliance with the general public’s interest
    Prepare a general development scheme and make sure that the project satisfies the specified requirements .
    Look after the safety, legal, commercial etc issues associated with the project.
    Look into the environmental, cultural and social effect that the project can cause,

## Slide 17: …….Continued
In Ethiopia, the major statutory bodies involved in the construction industry includes:
Municipalities: Bodies who are given the mandate to look after urban housing construction and its associated legalities;
the Ethiopian Road Authority: Besides being a major client of the road sector by itself, the ERA is the party mandated to look after the road sector construction works;
the Ministry of Water Resources; is the party mandated to overlook water sector development programs;
the Ministry of Works and Urban Development, the party mandated to regulate and promulgate bylaws, codes, standards, etc meant to promote efficiency, transparency, accountability as well as growth in the industry; Etc

## Slide 18: Other stakeholders
Suppliers: are parties that supply the varies materials, equipments and services needed for the project
Financers (Financial institutions): are donating or loaning agencies or institutions like banks, insurances, pension agencies etc who could provide loan services for the project
Works in the industry: are professionals, occupational or unskilled laborers who earn their living from working in the industry or its supply chain.
Trade Unions: Though not much visible in Ethiopian context, are unions of the working class that look after unfair treatment of workers (like payment issues, firing issues) as well as issues related to occupational health and safety.

## Slide 19: ……..Continued
Project product users: are parties who may be using the end product of the project
The general public: are communities of the locality, the general society of a country or even the globe who may have a vested interest in the project.
Other sectors: are sectors which could have interest in the process or product on the construction project